## Sheet1
Work Programme, Groundwater Governance
|  |  | 2005 | [11 empty] | 2006
|  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  | Lead | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Tasks
| Groundwater Book Writer's Workshop | MG
Develop key messages
Key messages debated
Contributing authors confirmed
Draft paragraph by paragraph outline
Group Workshop
Write first draft
Review first draft
Write second draft
Review second draft
Lead authors prepare final draft
Final approval
Editing and publishing
Milestones
First Draft of Key Messages
Final draft of key messages
Synopsis, final paragraph outline
First draft
CLA Workshop
Final draft
Manuscript to publisher
Report delivered