## Slide 1: Process and Timeline
The Comprehensive Assessment of Water Management in Agriculture

## Slide 2: Content of the assessment
Introduction and Conceptual Framework
Part 1: trends, conditions and response options – chapter on each question plus x-cut issues
Trends and condition
  50 years focusing on:
    benefits, costs, and impacts
Response Options
  Promising approaches
Part 2: scenarios – plausible futures, analyzes impact of various decisions
Part 3: policy overview

## Slide 3: Outline
Section 1
  Introduction
  Conceptual Framework
  Impacts of WMA
Section 2 –
  Rainfed
  Irrigated
  Groundwater
  Low Quality Water
  Fisheries
  Livestock
  Rice
  Land
  Basins
Section 3 –
  Water Productivity
  Ecosystems
  Policies & Institutions
  Poverty
Section 4
  Scenarios
Section 5
  Overview for Policy makers

## Slide 4: Teams
Chapter Teams – 3 to 4 lead authors for writing, contributing authors, network
Cross-cutting issue teams – same composition with additional responsibilities of interacting across chapters
Scenario Team – core team plus CLAs
Review Panel – independent, oversees review process
Secretariat – supports process

## Slide 5: Cross Cutting Issues
Ecosystems, Policies & Institutions, Climate Change, Poverty, Gender, and Health
Gender, Health, Climate Change incorporated across chapters
Small teams for gender and health to:
  Identify issues for chapters
  Provide content for chapters

## Slide 6: Cross – cutting teams
Poverty, Ecosystems, Policies & Institutions, Water Productivity
Synthesize material from chapters
Suggest material for chapters
One from each cross-cutting group should be involved in each chapter

## Slide 7: Scenarios
Team = lead authors plus specialist team
Chapters provide information to scenarios team
Scenario team requests chapter team for information
By September, prepare first draft for review at Synthesis meeting

## Slide 8: Chapters respond to:
Issues brought up by co-sponsors
Cross cutting themes – poverty, gender, health, environment, institutions
Scenario team

## Slide 10: Chapter Timeline
Jan-now: 2005: work plans finalized
March-June : Detailed outlines developed by on-line consultations and face-to-face meetings
July: first draft of chapters developed by lead author team
August: scientific review and feedback
September (week of 26th): synthesis workshop-integration
Oct to Nov - stakeholder consultation and 2nd draft
Nov to Dec - Second review

## Slide 11: Timeline - 2006
Jan to mid Feb - Final draft of chapters
Mid Feb to mid March –
  Final draft of scenarios and overview
  Presentation at 3rd World Water Forum
Mid March to May
  Final revisions based on final reviews
  Approval by co-sponsors, SC
May to July 2006 – substantive and scientific editing
Aug – Sep – publishing
August – delivery of overview document in Stockholm
October – delivery of Assessment

## Slide 12: Secretariat
Facilitates process –
Helps set up meetings, on-line discussions,
Maintains website
Communicates about the assessment to rest of world – issue/policy briefs, press releases
Coordinates publication
Fund raising

## Slide 13: Steering Committee
Patrick Dugan, Worldfish
Suhas Wani, ICRISAT
Eiman Karar, DWAF, South Africa
Johan Rockstrom, SEI, Sweden
Gina Castillo, Novib-Oxfam, Netherlands
Jean-Marc Faures, FAO
Bas Bouman, IRRI
Mark Rosegrant, IFPRI
Theib Oweis, ICARDA
David Molden, IWMI
Co-sponsors
FAO
RAMSAR

## Slide 14
Thank you
For further information visit: www.iwmi.org/assessment
or write to
comp.assessment@cgiar.org